AgentForge Change Control

Findings Remediation and Execution Plan

A structured, actionable, and trackable plan for implementing the refined PR governance service

| Field | Value |
| --- | --- |
| Prepared for | AgentForge product, platform, security, and engineering teams |
| Prepared date | 11 May 2026 |
| Scope | High-risk and agent-assisted pull request change control |
| Primary outcome | Every high-risk PR gets the right evidence, the right reviewers, and a recorded merge decision before it can merge |
| Execution model | Observe -> Warn -> Enforce -> Optimize |

Operating principle Deterministic checks decide. AI explains and assists. Humans approve risk.

# 1. Executive Summary

This document converts the identified product, engineering, and go-to-market findings into an executable remediation plan for AgentForge Change Control. The plan is designed for direct use by a cross-functional team building a GitHub-first merge governance service for high-risk and agent-assisted pull requests.

The refined direction is to avoid relying on perfect AI-generated PR detection. AgentForge should govern all high-risk PRs and apply additional scrutiny when agent-assistance signals are present. The first product, Merge Guard, should become a trusted required check that evaluates verified PR facts, applies explicit policies, requests evidence, routes reviewers, supports accountable overrides, and stores a Change Control Record.

Primary product promise High-risk PRs get the right evidence, the right reviewers, and a recorded merge decision before they can merge.

| Theme | Updated decision | Reason |
| --- | --- | --- |
| Scope | Govern all high-risk PRs; apply stricter controls to agent-assisted PRs | Avoids unreliable AI-only detection and makes the product useful for mixed human-agent workflows |
| MVP | Start with five deterministic checks | Creates high precision, explainability, and developer trust |
| Differentiator | Evidence-based merge control | More actionable and defensible than vague risk scoring |
| Trust model | Separate facts, claims, and judgments | Prevents overclaiming and improves enterprise credibility |
| Workflow | Observe -> Warn -> Enforce -> Optimize | Allows teams to adopt gradually without blocking engineering work prematurely |

# 2. Scope and Assumptions

This plan is scoped to AgentForge Change Control, specifically the first Merge Guard product line.

| In scope | Out of scope for V1 |
| --- | --- |
| GitHub App integration and PR webhooks | Full agent orchestration |
| Verified PR fact extraction | Autonomous merge decisions |
| Policy-as-code and policy packs | Full semantic architecture review |
| Evidence requirements and reviewer routing | Prompt/session replay unless an SDK is later adopted |
| Observe, warn, and enforce modes | IDE extension |
| Change Control Records and audit exports | Agentic blame or line-by-line authorship labeling |

Assumption 1: AgentForge begins as a GitHub-first product and later expands to GitLab, Bitbucket, and agent-provider SDKs.

Assumption 2: Blocking decisions in V1 must be based on verified facts and configured policies, not solely on LLM output.

Assumption 3: The first commercial buyer is likely Platform Engineering or DevSecOps at companies adopting coding agents.

# 3. Prioritization Framework

| Priority | Definition | Examples |
| --- | --- | --- |
| P0 | Must be solved for a credible private alpha or required check | Verified fact extractor, policy engine, five deterministic checks, Change Control Record |
| P1 | Required for enforce-mode beta and customer adoption | Evidence workflow, reviewer routing, override model, dashboard, Slack alerts |
| P2 | Improves usability, scale, or enterprise readiness | Policy packs, audit exports, policy versioning, retention controls |
| P3 | Strategic expansion after product-market validation | Agent provenance SDK, semantic coordination, multi-agent work graph |

| Severity | Definition | Action |
| --- | --- | --- |
| Critical | Blocks trust, safety, or adoption of the required check | Resolve before private alpha or enforce mode |
| High | Likely to create false positives, developer backlash, or compliance gaps | Resolve before beta enforcement |
| Medium | Limits usability, clarity, or scalability | Resolve during beta hardening |
| Low | Optimization or messaging refinement | Resolve before launch or after validated demand |

# 4. Findings Summary Matrix

| ID | Finding | Severity | Priority | Impacted areas | Resolution direction |
| --- | --- | --- | --- | --- | --- |
| F-01 | AI-only scope and detection are unreliable | Critical | P0 | Scope, policy engine, UX | Govern all high-risk PRs; agent signals increase scrutiny |
| F-02 | Blocking-first positioning creates adoption risk | High | P0 | Workflow, status checks | Implement observe/warn/enforce modes |
| F-03 | Risk scoring is less defensible than evidence-based control | High | P0 | Evidence engine, PR panel | Make required evidence the core product |
| F-04 | MVP remains too broad | High | P0 | Roadmap, engineering scope | Limit V1 to five deterministic checks |
| F-05 | Test weakening detection can be overclaimed | High | P0 | Diff analyzer, test scanner | Detect common patterns; escalate suspicious changes |
| F-06 | Reviewer routing can create noise | Medium | P1 | Reviewer router, UX | Use required, conditional, and suggested tiers |
| F-07 | Audit log needs compliance-grade structure | High | P1 | Record store, exports | Create Change Control Record with policy version |
| F-08 | Blank policy-as-code creates friction | Medium | P1 | Onboarding, policy packs | Ship opinionated policy templates |
| F-09 | LLM-based blocking would reduce trust | Critical | P0 | Decision engine, AI features | Use LLMs only for assistance in V1 |
| F-10 | Data-handling posture must be productized | Critical | P0 | Storage, security, compliance | Store metadata by default; configurable diff retention |
| F-11 | Dashboard must focus on action and governance | Medium | P1 | Dashboard, metrics | Prioritize blocked PRs, overrides, policy trends |
| F-12 | Pricing should align with protected assets | Medium | P2 | Packaging, GTM | Price by protected repos, retention, and policy depth |
| F-13 | Customer pain proof is still required | Critical | P0 | Discovery, roadmap | Validate required-check adoption and first policies |
| F-14 | Messaging must avoid liability-heavy safety claims | Medium | P1 | Marketing, UX copy | Use policy violation/change-control language |

# 5. System Impact Map

| System area | Responsibilities | Findings that affect it |
| --- | --- | --- |
| PR Fact Extractor | Parse PR metadata, changed paths, diffs, manifests, test changes, migrations, and CI changes | F-01, F-04, F-05, F-09, F-10 |
| Policy Engine | Evaluate verified facts against repo/org rules and mode settings | F-01, F-02, F-03, F-04, F-09 |
| Evidence Engine | Translate policy hits into required artifacts and completion states | F-03, F-07, F-08 |
| Reviewer Router | Assign required, conditional, and suggested reviewers | F-06, F-08, F-14 |
| Merge Guard Check Publisher | Publish pass/warn/block checks to GitHub | F-02, F-03, F-09, F-14 |
| Change Control Record Store | Persist policy version, findings, evidence, reviewers, overrides, and final decision | F-07, F-10 |
| Dashboard | Surface blocked work, policy trends, overrides, and adoption metrics | F-02, F-11, F-13 |
| Security and Data Layer | Retention, redaction, access control, audit exports, LLM controls | F-07, F-09, F-10 |
| Product/GTM | Positioning, pricing, discovery, policy packs, launch sequencing | F-08, F-12, F-13, F-14 |

# 6. Target V1 Architecture

The V1 architecture should be intentionally narrow. Each component should be testable independently and should treat verified PR facts as the source of truth for blocking decisions.

Architecture sketch

GitHub App -> Webhook Receiver -> PR Fact Extractor -> Policy Engine -> Evidence Engine -> Reviewer Router -> Merge Guard Check Publisher -> Change Control Record Store -> Dashboard + Notifications

| Component | Inputs | Outputs | Quality bar |
| --- | --- | --- | --- |
| Webhook Receiver | Pull request, review, check suite, and merge events | Normalized event envelope | Idempotent, replay-safe, authenticated |
| PR Fact Extractor | PR metadata, changed files, diffs, manifests | VerifiedFact[] | No LLM dependency; fixtures for all five checks |
| Policy Engine | Verified facts + policy file + mode | PolicyResult | Deterministic, explainable, under 60 seconds |
| Evidence Engine | Policy hits + PR metadata | EvidenceRequirement[] | Clear completion state and missing artifact detection |
| Reviewer Router | Policy hits + owners + existing reviews | Reviewer requests | Dedupe, tiering, no review explosions |
| Check Publisher | Policy result + evidence state | GitHub status check | Accurate pass/warn/block per mode |
| Record Store | Final evaluated state | Change Control Record | Immutable enough for audit; exportable |

# 7. Core Schema and Implementation Patterns

Core TypeScript-style types

type FindingSeverity = "critical" ¦ "high" ¦ "medium" ¦ "low"; type PolicyMode = "observe" ¦ "warn" ¦ "enforce"; type VerifiedFact = { id: string; type: ¦ "sensitive_path_changed" ¦ "ci_workflow_changed" ¦ "test_deleted" ¦ "test_skipped" ¦ "dependency_added" ¦ "dependency_bumped" ¦ "migration_added" ¦ "agent_signal_detected"; source: "github_diff" ¦ "github_metadata" ¦ "ci_status" ¦ "policy_config"; path?: string; evidence: string; confidence: "verified" ¦ "observed" ¦ "inferred" ¦ "attested"; }; type PolicyResult = { mode: PolicyMode; status: "pass" ¦ "warn" ¦ "block"; policyVersion: string; findings: VerifiedFact[]; requiredEvidence: EvidenceRequirement[]; requiredReviewers: ReviewerRequirement[]; explanation: string[]; };

Merge Guard evaluation flow

function evaluateMergeGuard(pr, policy): PolicyResult { const facts = extractVerifiedFacts(pr); const policyHits = applyPolicyRules(facts, policy); const evidence = deriveEvidenceRequirements(policyHits, pr); const reviewers = routeReviewers(policyHits, pr); const hasBlockingHit = policyHits.some(hit => hit.action === "block"); const missingEvidence = evidence.some(item => !item.satisfied); const missingRequiredReview = reviewers.some(item => !item.approved); const wouldBlock = hasBlockingHit ¦¦ missingEvidence ¦¦ missingRequiredReview; return { mode: policy.mode, status: policy.mode === "observe" ? "pass" : policy.mode === "warn" && wouldBlock ? "warn" : wouldBlock ? "block" : "pass", policyVersion: policy.version, findings: facts, requiredEvidence: evidence, requiredReviewers: reviewers, explanation: buildHumanReadableReasons(policyHits, evidence, reviewers) }; }

# 8. Detailed Findings and Remediation Tasks

## F-01. AI-only scope and detection are unreliable

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Critical | P0 | Policy engine, product positioning, PR fact extractor | Scope model, agent detection, policy schema, PR UX |

### Issue definition

The earlier product direction over-indexed on identifying AI-generated PRs. In practice, agent usage can be hidden, partial, copied into a human branch, or mixed with manual edits. A service that only governs clearly AI-generated PRs will miss high-risk work and create debate over whether a PR is agent-assisted enough to govern.

### Root cause

Agent involvement is not a reliable binary attribute. The product was framed around AI-generated PRs instead of change risk and policy applicability.

### Impact

Functionality: governance may not run on risky PRs if agent signals are absent.

Correctness: policy outcomes may depend on incomplete attribution signals rather than verified PR facts.

Maintainability: special-casing AI PRs creates complex and fragile detection logic.

Adoption: teams may resist a tool that depends on classifying developer work as AI-written.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F01-T1 | Update product scope so policies can apply to all PRs, selected repos, selected branches, or agent-assisted PRs. | Policy config supports apply_to: all_pull_requests and agent_assisted: stricter_controls. |
| F01-T2 | Implement agent signal detection as an input, not a gate. Signals include bot author, branch pattern, labels, commit metadata, PR markers, and user declaration. | Agent signals are recorded in findings but absence of signals does not bypass high-risk policy checks. |
| F01-T3 | Update PR panel language from 'AI PR result' to 'Merge Guard result'. | UI copy references policy findings and high-risk PRs rather than AI authorship as the core basis. |
| F01-T4 | Add policy tests showing a human-authored billing PR and an agent-authored billing PR both trigger billing controls, with stricter controls on the latter. | Unit and integration tests pass for both cases. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Human PR touches billing path | Run policy engine on a PR with no agent signals | Billing evidence and reviewer requirements still trigger. |
| Agent-assisted PR touches docs only | Run policy engine with agent signal but low-risk paths | No unnecessary block unless stricter agent doc policy is configured. |
| Mixed human-agent PR | Apply agent label to a PR with sensitive path changes | Both high-risk controls and stricter agent controls are evaluated. |

Policy configuration for all high-risk PRs with stricter agent-assisted controls

agentforge: mode: warn apply_to: - all_pull_requests agent_assisted: stricter_controls: true detection_signals: - bot_author - branch_pattern - ai_label - commit_metadata - pr_body_marker

### Implementation notes

Use agent detection to increase scrutiny, not to decide whether AgentForge runs.

Store agent signals in the Change Control Record for later audit without making authorship claims that cannot be proven.

## F-02. Blocking-first positioning creates adoption risk

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| High | P0 | Check publisher, policy mode configuration, dashboard | Workflow, GitHub checks, customer onboarding, developer experience |

### Issue definition

A required merge check is the correct long-term control point, but enforcing blocks immediately can create developer backlash if the system has not yet earned trust. Teams need a path to measure findings, tune policies, and move selected checks into enforcement gradually.

### Root cause

The previous plan emphasized blocking before defining a safe adoption path and policy maturity model.

### Impact

Functionality: teams may install AgentForge but avoid enabling required checks.

Maintainability: emergency policy exceptions may accumulate if enforcement is rushed.

Performance: noisy checks can increase review cycle time.

Adoption: developers may route around the tool if it slows low-risk work.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F02-T1 | Implement observe, warn, and enforce modes at org, repo, and policy-rule level. | Each mode produces correct GitHub check behavior and dashboard state. |
| F02-T2 | Create an onboarding sequence that recommends observe for 1-2 weeks, warn next, then enforce selected P0 rules. | Onboarding screens and docs describe the staged rollout. |
| F02-T3 | Add a mode-specific check publisher: observe always passes, warn posts non-blocking warnings, enforce blocks unmet policy requirements. | Integration tests verify status conclusions across all modes. |
| F02-T4 | Expose mode changes in the Change Control Record so audit reviewers know whether a finding was merely observed or enforced. | Records include mode and policy version. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Observe mode with policy violation | Open fixture PR that deletes tests | Status check passes but dashboard records finding. |
| Warn mode with policy violation | Open fixture PR that changes CI workflow | Non-blocking warning is posted; no merge block. |
| Enforce mode with missing evidence | Open migration PR without rollback plan | Required check blocks until evidence is added or override is recorded. |

Mode-to-status behavior

function publishStatus(policyResult) { if (policyResult.mode === "observe") return "success"; if (policyResult.mode === "warn") return "neutral"; if (policyResult.status === "block") return "failure"; return "success"; }

### Implementation notes

The first customer success milestone is movement from observe to enforce for at least one protected branch.

## F-03. Risk scoring is less defensible than evidence-based merge control

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| High | P0 | Policy engine, evidence engine, PR panel | Evidence workflow, status check explanations, reviewer experience |

### Issue definition

A numeric or vague risk score is easy to copy and hard to trust. The product becomes practical when it converts a finding into a concrete requirement: reviewer approval, rollback plan, dependency justification, benchmark, migration dry run, or deleted-test explanation.

### Root cause

The plan treated risk classification as a headline feature rather than a summary of enforceable policy and evidence requirements.

### Impact

Functionality: reviewers receive warnings without knowing exactly what action is required.

Correctness: teams may accept a PR because a score is low even when required process evidence is missing.

Maintainability: risk models can become opaque and difficult to tune.

Adoption: developers trust explicit missing requirements more than opaque scores.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F03-T1 | Build EvidenceRequirement objects derived from policy hits. | Every high-risk finding produces zero or more explicit evidence requirements. |
| F03-T2 | Update PR panel to show policy findings, missing evidence, required reviewers, and completion state before any risk score. | PR panel prioritizes actions and acceptance criteria. |
| F03-T3 | Implement evidence completion detection from PR checklist items, linked artifacts, review approvals, or manual attestations. | Evidence items move from missing to provided with timestamp and source. |
| F03-T4 | Define default evidence mapping for billing, auth, CI, dependency, migration, deleted-test, performance, and public API changes. | Policy packs include evidence mappings. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Billing path changed | Evaluate policy pack | Requires billing owner approval and rollback plan. |
| Dependency added | Modify package manifest | Requires dependency justification and configured security reviewer. |
| Evidence supplied | Add rollback plan marker to PR body or evidence form | Check updates from blocked to pass after all requirements are satisfied. |

Evidence requirement type

type EvidenceRequirement = { id: string; kind: ¦ "rollback_plan" ¦ "migration_dry_run" ¦ "dependency_justification" ¦ "deleted_test_explanation" ¦ "benchmark_before_after" ¦ "security_note"; status: "missing" ¦ "provided" ¦ "approved"; source?: "pr_body" ¦ "review" ¦ "attachment" ¦ "manual_attestation"; requiredByFindingId: string; };

## F-04. MVP remains too broad

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| High | P0 | Roadmap, engineering capacity, alpha scope | Product scope, sprint planning, QA fixtures |

### Issue definition

The product vision includes many valuable capabilities, but V1 must be narrow enough to ship, test, and trust. The initial MVP should focus on five deterministic checks that are easy to explain and difficult to dispute.

### Root cause

The broader platform vision was pulling advanced features such as semantic coordination, agent provenance, and orchestration into the initial build.

### Impact

Functionality: a wide MVP may deliver shallow checks instead of robust enforcement.

Correctness: under-tested detectors increase false positives and false negatives.

Maintainability: too many features create unclear ownership and slow iteration.

Performance: large feature surface can slow webhook processing and check publishing.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F04-T1 | Restrict V1 detectors to sensitive path changes, CI/deploy workflow changes, tests deleted/skipped, dependency added/bumped, and migration added. | Roadmap and sprint board explicitly exclude non-V1 detectors. |
| F04-T2 | Create fixture repositories and sample PR diffs for the five checks. | Each detector has positive, negative, and edge-case fixtures. |
| F04-T3 | Move semantic duplicate detection, prompt replay, agent orchestration, and agentic blame to V2+ backlog. | Backlog labels reflect phase and dependency. |
| F04-T4 | Define alpha exit criteria around precision, check latency, and required-check adoption, not feature count. | Alpha success metrics are documented and reviewed weekly. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Detector fixture suite | Run unit tests across all five detector categories | All fixture tests pass and detect expected facts only. |
| Large PR performance | Run extractor on PR with 500 changed files | Check completes under configured target or safely degrades. |
| Non-V1 feature request | Attempt to enable semantic detector | Feature remains disabled or advisory-only with clear labeling. |

V1 detector registry

const V1_DETECTORS = [ detectSensitivePathChanges, detectCiAndDeployChanges, detectDeletedOrSkippedTests, detectDependencyChanges, detectDatabaseMigrations, ];

## F-05. Test weakening detection can be overclaimed

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| High | P0 | PR diff analyzer, fixture corpus | Test scanner, policy engine, PR explanation copy |

### Issue definition

Deleting or skipping tests can be detected reliably, but subtle test weakening is difficult. The product should detect common test-weakening patterns and escalate suspicious test changes without claiming perfect understanding of test intent.

### Root cause

Earlier wording implied comprehensive test weakening detection, while many forms of weakened coverage require human judgment or deeper semantic analysis.

### Impact

Correctness: false negatives may miss subtle weakening, while false positives may frustrate reviewers.

Maintainability: complex semantic test analysis can become brittle across languages and frameworks.

Adoption: developers will distrust the tool if it confidently labels nuanced edits as weakened tests.

Functionality: common obvious cases still need deterministic detection and enforcement.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F05-T1 | Implement deterministic patterns for deleted test files, removed test cases, test.skip, it.skip, describe.skip, pytest.mark.skip, xdescribe, xit, and coverage threshold reductions. | Scanner emits verified or observed facts for each supported pattern. |
| F05-T2 | Label subtle assertion changes as suspicious_test_change instead of automatic block unless policy config enables blocking. | UI distinguishes common pattern from advisory suspicion. |
| F05-T3 | Add language/framework adapters for JavaScript/TypeScript first, then Python, Java, and Go as separate iterations. | Adapter coverage is tracked per language. |
| F05-T4 | Require deleted-test explanation and approving reviewer when tests are deleted or skipped under enforce mode. | Policy engine blocks until required evidence is provided. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| JS skipped test | Add it.skip to fixture | Fact test_skipped emitted and policy requires explanation. |
| Deleted test file | Remove test file from fixture PR | Fact test_deleted emitted with file path. |
| Assertion changed | Change expect(x).toEqual(y) to expect(x).toBeDefined() | Advisory suspicious_test_change only, unless strict policy configured. |

Common test-weakening patterns

const TEST_SKIP_PATTERNS = [ /\bit\.skip\s*\(/, /\btest\.skip\s*\(/, /\bdescribe\.skip\s*\(/, /\bxit\s*\(/, /\bxdescribe\s*\(/, /@pytest\.mark\.skip/, /\bpytest\.skip\s*\(/, ];

### Implementation notes

Use product language: 'Detects common test-weakening patterns' rather than 'proves tests were weakened.'

## F-06. Reviewer routing can create noise

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Medium | P1 | Policy hits, ownership mapping, GitHub reviewer API | Reviewer router, PR UX, ownership model |

### Issue definition

Routing every possible domain owner can create review paralysis. Reviewer routing must reduce coordination cost by deduplicating reviewers, distinguishing required from suggested review, and explaining why each reviewer is involved.

### Root cause

The previous plan treated reviewer routing as a simple mapping from risk domain to reviewer without accounting for overlap, review caps, or conditionality.

### Impact

Functionality: too many required reviewers can block otherwise valid PRs.

Performance: review cycles slow when unrelated teams are pulled in.

Maintainability: ownership maps become noisy and ignored if routing is imprecise.

Adoption: developers may view AgentForge as a bureaucracy multiplier.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F06-T1 | Introduce reviewer tiers: required, conditional, and suggested. | Reviewer router output includes tier and reason for each reviewer. |
| F06-T2 | Deduplicate team and individual reviewers and cap required reviewer groups per policy unless critical severity is present. | Routing tests verify no duplicate or excessive requests. |
| F06-T3 | Make conditional reviewers automatically clear when the triggering file change is removed from the PR. | Webhook sync updates reviewer requirements after PR changes. |
| F06-T4 | Display reviewer reasons in the PR panel. | Each reviewer requirement shows the triggering file, policy, and evidence requirement. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Multiple domains touched | PR touches billing and CI | Billing required; platform conditional if CI change remains; security suggested if dependency rule triggers. |
| Duplicate owner | Same team owns billing and checkout | Single reviewer request is emitted. |
| Trigger removed | PR initially modifies workflow, then removes workflow change | Platform conditional requirement is cleared. |

Reviewer router output structure

type ReviewerRequirement = { reviewer: string; tier: "required" ¦ "conditional" ¦ "suggested"; reason: string; triggeredByFindingId: string; clearsWhen?: "path_removed" ¦ "evidence_approved"; approved: boolean; };

## F-07. Audit log needs compliance-grade structure

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| High | P1 | Record store, policy versioning, check publisher | Audit, compliance, security review, final merge decision |

### Issue definition

A generic audit log is not enough for enterprise buyers. The service needs a structured Change Control Record that captures policy version, verified findings, evidence state, reviewer approvals, overrides, final decision, and timestamps.

### Root cause

The prior plan used 'audit log' language without defining the authoritative record that proves how and why a PR was allowed to merge.

### Impact

Functionality: teams cannot reconstruct merge decisions after incidents or audits.

Correctness: policy version at merge time may be lost if only current policy is stored.

Maintainability: unstructured logs are difficult to query and export.

Compliance: enterprise customers may reject the product without exportable decision records.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F07-T1 | Define ChangeControlRecord schema with policy version, mode, facts, evidence, reviewers, override, and final decision. | Schema approved by product, security, and platform leads. |
| F07-T2 | Persist a record on every evaluated PR and update it on policy re-evaluation, review approval, override, and merge. | Records show full lifecycle state transitions. |
| F07-T3 | Record override reason, actor, role, timestamp, and scope. | Override cannot be saved without reason under configured policies. |
| F07-T4 | Add CSV/JSON export for beta customers. | Export includes policy version and final decision fields. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Blocked then fixed | Open blocked PR, add evidence, pass, merge | Record shows blocked -> pass -> merged decision trail. |
| Override | Authorized user overrides missing evidence | Record includes actor, role, reason, timestamp, and policy version. |
| Policy update | Change policy after PR opened | Record retains policy version applied to each evaluation. |

Change Control Record example

{ "repo": "acme/checkout-service", "pr": 843, "mode": "enforce", "policyVersion": "fintech-v3.2", "verifiedFindings": ["billing_path_changed", "tests_deleted"], "requiredEvidence": { "rollback_plan": "provided" }, "requiredReviewers": ["billing-owner"], "decision": { "status": "merged_after_override", "overrideBy": "priya", "overrideReason": "Emergency production fix" } }

## F-08. Blank policy-as-code creates friction

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Medium | P1 | Policy engine, onboarding, policy templates | Onboarding, policy packs, customer success, documentation |

### Issue definition

Policy-as-code is powerful, but customers should not start from an empty YAML file. Teams need opinionated policy packs that encode common controls for startup, platform, fintech, healthcare, open-source, and strict enterprise workflows.

### Root cause

The previous plan emphasized configurable policy but underweighted the initial customer setup experience.

### Impact

Functionality: customers may install the product but fail to configure meaningful rules.

Maintainability: ad hoc policies across customers become harder to support.

Adoption: onboarding friction slows movement from observe to enforce.

Correctness: poorly written policies can miss critical paths or overblock low-risk PRs.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F08-T1 | Create initial policy packs: Startup Default, Platform Engineering, Fintech, Healthcare/Regulated, Open Source Maintainer, Enterprise Strict. | Each pack includes sensitive paths, evidence requirements, reviewer routing, and default mode. |
| F08-T2 | Build onboarding flow that asks customer to choose a pack and map owners for security, platform, billing, and database domains. | Customer can complete setup without writing YAML manually. |
| F08-T3 | Add policy preview using recent PRs to show which findings would have triggered. | Observe-mode preview displays expected policy hits without blocking. |
| F08-T4 | Version policy packs and allow customers to fork them. | Policy pack version is stored in Change Control Records. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Startup pack | Apply to standard fixture repo | Only tests, CI, dependencies, migrations, and configured sensitive paths trigger. |
| Fintech pack | Apply to checkout fixture | Billing and payment changes require rollback plan and domain owner. |
| Policy preview | Run pack against historical PRs | Results match policy engine output in observe mode. |

Policy pack selection model

type PolicyPack = { id: "startup_default" ¦ "platform" ¦ "fintech" ¦ "regulated"; version: string; defaultMode: "observe" ¦ "warn" ¦ "enforce"; rules: PolicyRule[]; requiredOwnerMappings: string[]; };

## F-09. LLM-based blocking would reduce trust

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Critical | P0 | Decision engine, AI features, product copy | AI assistant layer, policy engine, status checks, trust model |

### Issue definition

LLMs can help summarize, explain, and identify advisory risks, but V1 blocking decisions must not depend solely on generated judgments. Deterministic facts and explicit policies should decide whether a PR passes, warns, or blocks.

### Root cause

The product category could be confused with AI code review if LLM output is allowed to drive trust-critical outcomes.

### Impact

Correctness: LLM hallucinations may block valid PRs or miss policy violations.

Maintainability: generated reasons can change unpredictably across model versions.

Adoption: enterprise buyers need explainable and reproducible controls.

Compliance: audit records must show configured policy, not opaque AI judgment, as the basis for blocking.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F09-T1 | Add explicit source and confidence to all findings: verified, observed, inferred, or attested. | Policy engine blocks only on configured verified/observed findings in V1. |
| F09-T2 | Implement LLM output as advisory metadata with separate display section. | LLM suggestions cannot set status=block unless backed by a deterministic policy hit. |
| F09-T3 | Add customer setting to disable LLM features entirely. | Product operates fully with deterministic checks only. |
| F09-T4 | Document product posture: deterministic checks decide; AI explains and assists; humans approve risk. | Docs and UI copy consistently use this language. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| LLM unavailable | Disable model service | Policy checks still run and publish correct result. |
| LLM flags duplicate helper | Advisory finding emitted | No block unless separate deterministic policy violation exists. |
| Deterministic block | CI workflow modified under enforce mode | Block occurs even if LLM summary is absent. |

Guardrail against LLM-only blocking

function canBlock(finding: Finding): boolean { return finding.confidence === "verified" ¦¦ finding.confidence === "observed"; } const blockingFindings = findings.filter(f => policy.blocks(f.type) && canBlock(f) );

## F-10. Data-handling posture must be productized

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Critical | P0 | Storage design, security review, enterprise roadmap | Data retention, secrets handling, source code access, LLM controls |

### Issue definition

AgentForge will touch sensitive engineering data. The product must store metadata by default, make full-diff retention configurable, redact secrets, avoid training on customer code, and support enterprise deployment options later.

### Root cause

The product requires access to PR metadata and diffs, but previous planning did not fully translate data sensitivity into implementation requirements.

### Impact

Security: accidental source or secret retention can create unacceptable risk.

Compliance: regulated customers may reject the tool without retention and export controls.

Maintainability: unclear data boundaries complicate support, logs, and incident response.

Adoption: enterprise security review will block procurement if data posture is vague.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F10-T1 | Store metadata by default: repo, PR number, file paths, findings, policy results, reviewer state, evidence state, and overrides. | Default database schema excludes full source content. |
| F10-T2 | Make full-diff retention opt-in and configurable by repo/org. | Customers can choose no diff retention, short retention, or extended retention. |
| F10-T3 | Redact secrets from logs, stored snippets, and LLM prompts if LLM features are enabled. | Secret-like strings are masked in test logs and stored artifacts. |
| F10-T4 | Add customer-facing data-handling documentation before beta. | Docs answer what is stored, retained, exported, and never used for model training. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Default storage | Run PR evaluation | Database contains metadata and no source blobs. |
| Secret in diff | Fixture includes token-like string | Stored output and logs redact value. |
| LLM disabled | Customer setting disables LLM | No prompts are generated; checks still pass. |

Retention settings

data_retention: source_code_storage: false full_diff_retention: "disabled" # disabled ¦ 7d ¦ 30d ¦ custom redact_secrets: true llm_features: false audit_record_retention: "365d"

## F-11. Dashboard must focus on action and governance

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Medium | P1 | Record store, event ingestion, policy results | Dashboard, analytics, customer success, executive reporting |

### Issue definition

A dashboard that lists all PRs will not help buyers. The first dashboard should show blocked work, policy violations, overrides, agent-assisted change volume, risk by repository, and evidence completion trends.

### Root cause

The earlier dashboard idea was broad and PR-centric rather than action-centric and governance-oriented.

### Impact

Functionality: users may not know what needs action immediately.

Performance: dashboards that query all PRs at high granularity may be slow and noisy.

Adoption: platform/security buyers need governance views, not another PR inbox.

Maintainability: broad analytics without clear jobs-to-be-done can sprawl quickly.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F11-T1 | Build dashboard sections: Blocked PRs, Policy Violations, Overrides, Agent-Assisted Changes, Risk by Repository, Evidence Completion. | Dashboard home page prioritizes blocked PRs and missing actions. |
| F11-T2 | Add filters by repo, policy pack, mode, team, severity, and time range. | Users can isolate current blockers and policy trends. |
| F11-T3 | Display override rate and top override reasons. | Security/platform leads can audit policy bypass behavior. |
| F11-T4 | Avoid showing low-risk PRs by default. | Dashboard noise stays low unless user expands scope. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Blocked PR view | Seed records with mixed statuses | Only blocked and action-required PRs appear by default. |
| Override trend | Seed override records | Dashboard aggregates actors, reasons, and policies. |
| Filter by repo | Apply repo filter | All widgets update consistently. |

Dashboard information hierarchy

DashboardHome - BlockedPRs(action_required=true) - PolicyViolations(group_by=rule_id) - Overrides(group_by=actor, reason, policy) - AgentAssistedChanges(by_repo, by_week) - EvidenceCompletion(by_requirement_kind)

## F-12. Pricing should align with protected assets

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Medium | P2 | Packaging, sales validation, analytics | Pricing, packaging, business model, usage metering |

### Issue definition

Per-seat pricing may not align with value because coding agents can increase PR volume without increasing human seats. Pricing should anchor on protected repositories, audit retention, policy sophistication, and later governed agent sessions.

### Root cause

The previous pricing model included per-developer pricing despite the protected asset being the repository and merge workflow.

### Impact

Business model: per-seat pricing may undercharge high-volume agent workflows or overcharge small teams.

Adoption: repo-based pricing maps better to the buyer's mental model of what is protected.

Maintainability: feature entitlements need clear packaging across Free, Team, Business, Enterprise, and Platform API.

Performance: usage analytics must track protected repos, checks, retention, and sessions.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F12-T1 | Define packaging around protected repositories, policy packs, audit retention, SSO/VPC, and exports. | Pricing page and internal billing schema reflect protected asset model. |
| F12-T2 | Add metering for protected repos, evaluated PRs, policy checks, audit retention, and optional agent sessions. | Billing events can be generated from product usage. |
| F12-T3 | Validate willingness-to-pay with design partners during observe-mode rollout. | Pricing hypotheses are tested before public launch. |
| F12-T4 | Keep Free plan warn-only for one repo to support OSS and demos. | Free plan cannot become enforce-mode across many protected repos. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Plan entitlement | Configure Free plan with two protected repos | Second repo enforcement is denied or prompts upgrade. |
| Retention entitlement | Set 365-day retention on Team plan if not allowed | Product surfaces plan requirement. |
| Metering event | Run policy evaluation | Usage event records repo, check, and plan context. |

Packaging dimensions

Plan dimensions: protected_repos policy_packs audit_retention_days enforce_mode_enabled sso_enabled vpc_or_self_hosted audit_exports governed_agent_sessions

## F-13. Customer pain proof is still required

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Critical | P0 | Discovery interviews, alpha design partners | Product validation, roadmap, GTM, success metrics |

### Issue definition

The plan is strategically coherent, but the company depends on whether teams will install AgentForge and eventually make it a required check. Before broad buildout, the team must validate exact buyer pain, enforceable policies, false-positive tolerance, and override ownership.

### Root cause

The current plan is based on strong reasoning but still needs empirical confirmation from target customers.

### Impact

Functionality: the product may build checks that customers do not enforce.

Maintainability: roadmap may expand before the core wedge is validated.

Business performance: sales cycles may stall if the buyer or budget owner is wrong.

Adoption: low willingness to make it a required check would invalidate the wedge.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F13-T1 | Interview at least 30 target stakeholders: platform engineering, DevSecOps, AI adoption teams, OSS maintainers, and compliance-sensitive engineering leaders. | Research notes summarize top policies, buyer, blocker, and adoption path. |
| F13-T2 | Ask required-check validation questions directly, including whether they would run observe, warn, and enforce modes. | Interview script includes required-check adoption and false-positive tolerance. |
| F13-T3 | Recruit 3-5 private alpha design partners willing to install the GitHub App in observe or warn mode. | Design partner agreements or written commitments exist before beta scope expands. |
| F13-T4 | Define alpha success metrics: required-check adoption, false-positive rate, time-to-result, policies moved to enforce, and expansion to more repos. | Metrics dashboard is reviewed weekly. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Interview evidence | Review discovery notes | At least five customers name the same first policies to enforce. |
| Design partner install | Install GitHub App in observe mode | Partner sees findings on real repos within first week. |
| Required-check adoption | Move one P0 policy to enforce | Customer keeps it enabled for protected branch after trial. |

Discovery question checklist

1. Would you install a PR governance check for agent-assisted work? 2. Would you run it in observe mode first? 3. Which policies would you enforce immediately? 4. What false-positive rate would make you uninstall it? 5. Who is allowed to override a block? 6. Do you want all high-risk PRs governed, or only agent-assisted PRs?

## F-14. Messaging must avoid liability-heavy safety claims

| Severity | Priority | Dependencies | Primary system areas |
| --- | --- | --- | --- |
| Medium | P1 | Product copy, PR panel, website, documentation | Messaging, UI language, legal review, enterprise trust |

### Issue definition

The product should not claim to prove code is safe or unsafe. It should state whether a PR satisfies configured change-control policies. This language is more accurate, more enterprise-friendly, and less likely to create liability or developer pushback.

### Root cause

Earlier phrases such as 'AI PR Firewall' and 'unsafe PR' could imply security guarantees or adversarial posture.

### Impact

Correctness: safety claims may overstate what deterministic policy checks can prove.

Adoption: developers may resist language that labels their work unsafe.

Compliance: legal/security review may object to unsupported guarantees.

Maintainability: product copy must remain consistent across UI, docs, alerts, and sales material.

### Required actions

| Task ID | Action | Acceptance criteria |
| --- | --- | --- |
| F14-T1 | Replace 'unsafe PR' wording with 'policy-violating PR', 'missing required evidence', or 'change-control finding'. | UI, docs, and alerts use consistent terminology. |
| F14-T2 | Use 'Merge Guard' or 'Change Control' in product names; reserve 'firewall' only for informal marketing if at all. | Product surfaces do not use firewall as a formal module name. |
| F14-T3 | Add legal/security review for public website copy and enterprise security documentation. | Approved copy is stored in launch checklist. |
| F14-T4 | Create message templates for pass, warn, block, override, and evidence-required states. | Templates are tested in PR panel and Slack alerts. |

### Testing and validation

| Scenario | Validation method | Regression / edge checks |
| --- | --- | --- |
| Copy lint | Scan product strings | No banned terms such as 'guaranteed safe' or 'AI wrote bad code' appear. |
| Blocked PR alert | Trigger policy block | Alert says which policy requirement is unmet, not that code is unsafe. |
| Override message | Apply override | PR shows actor, reason, and policy context without blame language. |

Preferred language mapping

Avoid: "AgentForge blocked unsafe AI code." Use: "Merge Guard blocked merge because required policy evidence is missing." Avoid: "AI risk score is high." Use: "Change-control findings require billing owner approval and rollback plan."

# 9. Iterative Delivery Workflow

All remediation work should follow an iterative loop. Each change must move through implementation, automated validation, review, customer feedback, and refinement until the finding is fully closed.

Recommended remediation loop

Implement fix -> Run unit and fixture tests -> Run integration checks against GitHub webhook fixtures -> Review PR with product + platform/security owner -> Deploy to internal/staging environment -> Validate on design partner or demo repo -> Capture feedback and false positives -> Refine policy, detector, copy, or workflow -> Record completion against finding acceptance criteria

| Iteration stage | Required output | Owner |
| --- | --- | --- |
| Plan | Task selected with priority, dependency, acceptance criteria, and test plan | Product + Engineering Lead |
| Implement | Code change, schema change, policy update, or copy update | Assigned engineer or product owner |
| Validate | Unit, integration, fixture, and E2E checks pass | QA + Engineer |
| Review | Product, platform, security, or GTM review depending on finding | Designated reviewer |
| Pilot | Observed on demo repo or design partner repo | Customer Success + Engineering |
| Refine | False positives and friction corrected | Feature owner |
| Close | Acceptance criteria met and Change Control Record updated | Engineering Lead |

# 10. Implementation Roadmap and Dependencies

| Sprint / Phase | Primary deliverables | Findings addressed | Exit criteria |
| --- | --- | --- | --- |
| Sprint 0: Validation | Interviews, design partners, top policy list, first policy schema | F-13, F-12, F-14 | 3-5 design partners; top five policies confirmed |
| Sprint 1: Foundation | GitHub App, webhook receiver, PR fact extractor, policy engine, check publisher | F-01, F-02, F-04, F-09, F-10 | Observe/warn checks publish reliably on demo repo |
| Sprint 2: Deterministic checks | Sensitive path, CI/deploy, tests, dependencies, migrations | F-04, F-05 | Fixture suite passes; check latency target met |
| Sprint 3: Evidence + reviewers | Evidence engine, reviewer routing tiers, override workflow | F-03, F-06, F-07 | Enforce mode can block and unblock correctly |
| Sprint 4: Policy packs + dashboard | Policy templates, onboarding, blocked PR dashboard, override trends | F-08, F-11, F-14 | Design partners can configure without blank YAML |
| Sprint 5: Beta hardening | Audit export, data docs, retention settings, customer feedback refinement | F-07, F-10, F-13 | At least one customer uses required check on protected branch |

Critical path F-13 customer validation and F-10 data-handling posture must run in parallel with engineering foundation work. Do not expand beyond the five deterministic checks until design partners validate required-check adoption.

# 11. Consolidated Testing and Validation Strategy

Testing must prove that AgentForge is accurate, fast, explainable, and safe to operate in customer repositories.

| Test layer | Purpose | Required coverage |
| --- | --- | --- |
| Unit tests | Validate detectors, policy evaluation, evidence derivation, reviewer routing, and status mapping | Each detector has positive, negative, and edge-case fixtures |
| Integration tests | Validate GitHub webhook ingestion, check publishing, review updates, and PR synchronization | PR opened, synchronize, review submitted, check suite, merge events |
| End-to-end tests | Validate full lifecycle from PR open to block, evidence completion, approval, override, and merge record | At least one E2E scenario for each of the five checks |
| Regression fixtures | Prevent known false positives/negatives from returning | Fixture corpus grows whenever a customer reports an issue |
| Performance tests | Ensure checks complete quickly on large PRs | Target under 60 seconds for normal PRs; graceful degradation for very large diffs |
| Security tests | Ensure no secrets or source code are retained unexpectedly | Secret redaction, no-code-retention mode, LLM-disabled mode |
| UX validation | Ensure explanations are actionable and low-noise | Design partner review of blocked/warned PR messages |

Representative test cases

describe("Merge Guard policy engine", () => { it("blocks deleted tests in enforce mode", () => { const pr = fixture("deleted-test-file"); const policy = policyPack("startup_default", { mode: "enforce" }); const result = evaluateMergeGuard(pr, policy); expect(result.status).toBe("block"); expect(result.findings).toContainFact("test_deleted"); expect(result.requiredEvidence).toContainKind("deleted_test_explanation"); }); it("warns but does not block in warn mode", () => { const pr = fixture("ci-workflow-change"); const policy = policyPack("platform", { mode: "warn" }); const result = evaluateMergeGuard(pr, policy); expect(result.status).toBe("warn"); }); });

| Scenario | Expected result | Regression checks |
| --- | --- | --- |
| PR changes only README | Pass in all default packs | No reviewer routing, no evidence requirement |
| PR changes checkout billing path | Requires billing owner and rollback plan | Agent signals do not change base requirement; may add stricter controls |
| PR modifies .github/workflows/deploy.yml | Requires platform owner or blocks if configured | Removing workflow change clears conditional review |
| PR deletes test file | Requires deleted-test explanation and approval | Observe mode records only; enforce mode blocks |
| PR adds dependency | Requires dependency justification and security/license check if configured | Lockfile-only churn is classified separately |
| PR adds db migration | Requires rollback plan and dry run | Migration path aliases are detected |
| PR includes secret-like token | Redacts stored/logged values | No full source retention by default |

# 12. Trackable Issue Register

Use the table below as a lightweight execution tracker. Status should be updated at least weekly during alpha and beta.

| ID | Finding | Priority | Status | Owner | Target date |
| --- | --- | --- | --- | --- | --- |
| F-01 | AI-only scope and detection are unreliable | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-02 | Blocking-first positioning creates adoption risk | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-03 | Risk scoring is less defensible than evidence-based merge control | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-04 | MVP remains too broad | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-05 | Test weakening detection can be overclaimed | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-06 | Reviewer routing can create noise | P1 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-07 | Audit log needs compliance-grade structure | P1 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-08 | Blank policy-as-code creates friction | P1 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-09 | LLM-based blocking would reduce trust | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-10 | Data-handling posture must be productized | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-11 | Dashboard must focus on action and governance | P1 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-12 | Pricing should align with protected assets | P2 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-13 | Customer pain proof is still required | P0 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |
| F-14 | Messaging must avoid liability-heavy safety claims | P1 | [ ] Not started [ ] In progress [ ] Blocked [ ] Done |  |  |

# 13. Definition of Done

A finding is not closed until product behavior, implementation, tests, and operational evidence are complete.

The issue has a documented owner, priority, dependency, and acceptance criteria.

The code, configuration, copy, or process change has been implemented.

Unit, integration, fixture, and relevant E2E tests pass.

The behavior has been validated on a demo or design partner repository where applicable.

Any customer-facing copy uses change-control language and avoids unsupported safety claims.

The Change Control Record captures the final outcome for any PR-level behavior.

False-positive risks and known limitations are documented.

Product, platform, and security owners agree the finding is resolved or intentionally deferred.

# Appendix A. Example Full Policy File

version: 1 agentforge: mode: warn apply_to: - all_pull_requests agent_assisted: stricter_controls: true detection_signals: - bot_author - branch_pattern - ai_label - commit_metadata - pr_body_marker sensitive_paths: billing: paths: - "src/billing/**" - "src/checkout/**" - "services/payments/**" required_reviewers: - "billing-owner" required_evidence: - "rollback_plan" auth: paths: - "src/auth/**" - "services/identity/**" required_reviewers: - "security-team" required_evidence: - "security_note" ci_and_deploy: paths: - ".github/workflows/**" - "scripts/deploy/**" - "infra/prod/**" required_reviewers: - "platform-team" block_for_agent_assisted: true tests: deleted_tests: action: block required_evidence: - "deleted_test_explanation" skipped_tests: action: block patterns: - "test.skip" - "it.skip" - "describe.skip" - "@pytest.mark.skip" dependencies: new_package: action: require_review required_reviewers: - "security-team" required_evidence: - "dependency_justification" major_version_bump: action: require_review database: migrations: paths: - "db/migrations/**" - "migrations/**" required_reviewers: - "database-owner" required_evidence: - "rollback_plan" - "migration_dry_run" overrides: allowed_roles: - "engineering_manager" - "platform_admin" require_reason: true visible_in_pr: true audit: true

# Appendix B. Example GitHub Check Output

AgentForge Merge Guard: Blocked Mode: Enforce Policy version: fintech-v3.2 Policy findings: - Billing path changed: src/billing/checkout.ts - Deploy workflow changed: .github/workflows/deploy.yml - 2 tests deleted - New dependency added: fast-cache-lib Required evidence: - Rollback plan: missing - Deleted-test explanation: missing - Dependency justification: missing Required reviewers: - Billing owner: pending - Platform owner: pending This check blocks merge because required policy evidence and approvals are missing.

# Appendix C. Launch Readiness Checklist

| Area | Launch-readiness item | Status |
| --- | --- | --- |
| Product | Observe, warn, and enforce modes are implemented | [ ] |
| Product | Policy packs are available for Startup Default, Platform, and Fintech | [ ] |
| Engineering | Five deterministic detectors pass fixture regression suite | [ ] |
| Engineering | GitHub status check publishes correct result in all modes | [ ] |
| Security | Default storage excludes source code and full diffs | [ ] |
| Security | Secret redaction tests pass | [ ] |
| Compliance | Change Control Record export is available | [ ] |
| UX | Blocked PR explanations are actionable and non-accusatory | [ ] |
| GTM | Design partner case study or pilot evidence is available | [ ] |
| GTM | Pricing and packaging are validated with at least three prospects | [ ] |